## Bug Tracker
🐛 BUG TRACKING TOOL
Project Bug Register ¦ Last Updated: 30 Apr 2026
Bug ID | Title / Summary | Module / Component | Severity | Priority | Status | Reported By | Date Reported | Assigned To | Target Fix Date | Date Resolved | Environment | Steps to Reproduce | Expected Result | Actual Result | Comments / Notes
BUG-001 | Login button unresponsive on mobile | Authentication | Critical | P1 | In Progress | Rajesh K. | 2024-04-01 | Dev Team A | 2024-04-05 |  | Production | 1. Open app on iOS 2. Tap Login | Login page loads | Button does nothing | Reproduced on iPhone 14
BUG-002 | Dashboard data not refreshing automatically | Dashboard | High | P2 | Open | Priya S. | 2024-04-02 | Dev Team B | 2024-04-07 |  | Staging | 1. Login 2. Wait 5 min | Auto-refresh every 60s | Data stays stale | Needs WebSocket fix
BUG-003 | Export CSV produces garbled characters | Reports | Medium | P2 | Resolved | Amit T. | 2024-03-28 | Dev Team A | 2024-04-03 | 2024-04-03 | QA | 1. Go to Reports 2. Export CSV | Clean UTF-8 file | Special chars corrupted | Fixed encoding to UTF-8
BUG-004 | Typo in user profile page | UI / Profile | Low | P4 | Closed | Sunita R. | 2024-03-25 | Dev Team C | 2024-04-01 | 2024-04-01 | Staging | 1. Go to Profile 2. Check heading | Correct spelling | "Profle" shown | Quick CSS fix applied
BUG-005 | Password reset email not sent | Email Service | Critical | P1 | Open | Naveen M. | 2024-04-03 | Dev Team B | 2024-04-06 |  | Production | 1. Click Forgot Password 2. Enter email | Email arrives in 2 min | No email received | SMTP config suspect

## Dashboard
📊 BUG TRACKER – DASHBOARD
Auto-calculated summary from Bug Tracker sheet
BUGS BY STATUS | BUGS BY SEVERITY
Open | Critical
In Progress | High
Resolved | Medium
Closed | Low
Deferred
TOTAL
QUICK STATISTICS
Total Bugs Logged
Critical Bugs Open
Bugs Resolved Today
Avg Days to Resolve

## How to Use
📖 HOW TO USE THIS BUG TRACKER
FIELD | DESCRIPTION
Bug ID | Unique identifier. Use format BUG-001, BUG-002 …
Title / Summary | One-line description of the issue
Module / Component | Area of the app affected (e.g. Login, Dashboard)
Severity | Critical / High / Medium / Low (use dropdown)
Priority | P1 = Urgent … P4 = Low (use dropdown)
Status | Open → In Progress → Resolved → Closed (use dropdown)
Reported By | Name of person who found the bug
Date Reported | Date bug was first reported (YYYY-MM-DD)
Assigned To | Developer or team responsible for fixing
Target Fix Date | Expected resolution date
Date Resolved | Actual date the bug was fixed
Environment | Production / Staging / QA / Development / UAT
Steps to Reproduce | Numbered steps to trigger the bug
Expected Result | What should happen
Actual Result | What actually happens
Comments / Notes | Any extra info, links, screenshots references
TIP | Use the filters in Row 3 to slice by Status, Severity, or Assignee.
TIP | Check the Dashboard sheet for live summary counts.
TIP | Sort by Priority (Col E) to see most urgent bugs first.